Developer Constructed Project Closeout Report Guidance Notes

Guidance notes in blue text have been prepared to assist with the preparation of the Closeout Report and must be deleted before submitting the report. They are present throughout the template for general guidance to assist with writing the report. The report must be submitted as a single consolidated document in pdf format only. After Water Corporation has provided comments on the initial report, all changes to further revisions shall be shown on a Review Response Table as an appendix of the Closeout Report.

The significance and purpose of a Closeout Report

Acceptance of the Closeout Report is required for the Water Corporation Project Practical Completion (PPC) milestone.

It contains all the information to effectively close the project out and allow the recoup period (if a recoup is applicable) to commence in accordance with the Developer Constructed Works Agreement (DCWA).

The timing of the recoup to the developer is dependent on the acceptance of this Closeout Report. It shall be submitted no later than 6 weeks after Final Inspection has been issued.

Further subdivision clearance requests may be impacted until the Closeout Report is submitted and capable of acceptance which includes any land matters being resolved and all as-constructed drawings provided.

Template revision date is 16/01/20 – version 2

DEVELOPER CONSTRUCTED PROJECT CLOSEOUT REPORT

Insert Project Name Here

Project Number: Insert Here

Developer: Insert Here

Consultant: Insert Here

Date: Insert Here

| Sign Off | Signatory | Signed | Date |
| --- | --- | --- | --- |
| Report Prepared Developer’s consultant PM |  |  |  |
| Report Reviewed Water Corporation PM |  |  |  |
| Report Reviewed Water Corporation PD |  |  |  |
| Report Endorsed Water Corporation Program Manager |  |  |  |

| Revision | Date |
| --- | --- |
| Initial |  |
| Final or Revision 2 (amend as required) |  |

Update contents on completion of report - Right click over body of contents / update field / update entire table.

Contents

1.	Project Scope	4

2.	Delivery Strategy	4

3.	Project Costs – see notes listed below table	4

4.	Time	5

5.	Approved Scope Changes	6

6.	Performance Against Key Objectives	6

7.	Community and Stakeholder Issues & Regulatory Approvals	6

8.	Highlights and Innovations	6

9.	Outstanding Project Completion Actions	6

10.	Lessons Learned Items	7

11.	Defects Liability Period	7

12.	Warranties	7

Appendices	8

Appendix 1 – Works Paid Confirmation Letter	8

Appendix 2 – Water Corporation cost summary template	8

Water Corporation cost estimate spreadsheet updated with actual costs	8

Appendix 3 – Construction Contract Variation Table	8

Appendix 4 – Engineering Fees and Variation Table	8

Appendix 5 – Engineering Fee Tax Invoices	8

Appendix 6 – Construction Engineer Statement	8

Appendix 7 – Land Restoration Letter	8

Appendix 8 – Land Matters, Survey Plan and Land Transfer Documentation	8

Appendix 9 – Design Compliance Report	8

Appendix 10 – Warranties	8

Appendix 11 – Construction Schedule/Timeline	8

Appendix 12 – As Constructed Drawings List	8

Appendix 13 – Project Photos	8

Appendix 14 – Developer Project Monthly Progress Reports	9

Appendix 15 – Closeout Report Administration Sheet	9

Appendix 16 – Closeout Report Review Response Table	9

- Project Scope

This brief description of the project scope should only contain the Corporation’s capital project elements from the ESR and Detailed Design.

- Delivery Strategy

Project delivered as per the developer constructed process.

- Project Costs – see notes listed below table

| Item | Estimate (at ESR, including contingencies) | Actual | Fully WC reimbursable | Not WC reimbursable |
| --- | --- | --- | --- | --- |
| Scoping Report |  |  |  |  |
| Engineers Costs |  |  |  |  |
| Others: |  |  |  |  |
| ??? |  |  |  |  |
| ESR & Detailed Design |  |  |  |  |
| Engineers Costs |  |  |  |  |
| Others: |  |  |  |  |
| Survey |  |  |  |  |
| Geotech |  |  |  |  |
| Asbestos |  |  |  |  |
| Environmental |  |  |  |  |
| Construction Admin |  |  |  |  |
| Engineers Costs |  |  |  |  |
| Others: |  |  |  |  |
| ??? |  |  |  |  |
| Construction Costs |  |  |  |  |
| Engineers Costs |  |  |  |  |
| Others: |  |  |  |  |
| Total Project Costs (excluding GST) |  |  |  |  |

Cost Summary Notes

- Engineers costs represent the Developer’s consultant driving the project, hence the reason

for inclusion under construction as they prepare the estimate.

- Others under Scoping Report/ESR and Construction Administration are any other consultants hired to complete specific functions not covered by the Developer’s consultant.

- Others under construction costs is for the contractors cost, expanding the rows if there are more than one

- Each section is to be sub-totalled, with an overall project total

- Actual is the overall figures, broken into reimbursable or not if the scope of the work was greater than just works defined in the Detailed Design.

- If there are "gifted" assets, e.g. no cost to the Corporation but will ultimately be under Water Corp responsibility, these should be identified separately in the ‘Not WC Reimbursable’ column with a real value given.

  - Reasons for Cost variance

Provide detailed information on the variance between estimated cost in the Engineering Summary Report and the actual cost. This should be based on variation requests submitted to the Corporation’s Project Manager for approval which are documented in the monthly reports.

- Time

| Milestone | Estimation at Scoping Report | Estimation at ESR/Detailed Design | Estimation at Construction Contract Award | Actual |
| --- | --- | --- | --- | --- |
| Scoping Report Endorsed |  |  |  |  |
| DCWA Signed |  |  |  |  |
| ESR Signed Off |  |  |  |  |
| PtW commenced |  |  |  |  |
| PtW completed |  |  |  |  |
| Detailed Design Signed Off |  |  |  |  |
| Tender Recommendation Accepted |  |  |  |  |
| Contract Award |  |  |  |  |
| Start-Up Meeting |  |  |  |  |
| Commissioning |  |  |  |  |
| Final Inspection |  |  |  |  |
| Construction Contract PC |  |  |  |  |
| As-Cons Lodged |  |  |  |  |
| Asset Handover Checklist Requirements Complete |  |  |  |  |
| Project Closeout Report Acceptance* |  |  |  |  |

*Project Closeout Report acceptance is Water Corporation’s Project Manager acceptance.

  - Reasons for Time variance

Provide comments on reasons for time variance. As the process has recently changed (2019) the expected durations and responsibilities of certain milestones, the time variance is crucial to refine KPI’s and responsibilities of both the Corporation and Developer’s consultant.

- Approved Scope Changes

Particularly highlight if the variance has been impacted by issues such as land matters, environmental, native title or aboriginal heritage. E.g. describe how these issues have affected the project if such is the case, or note that they did not affect the project delivery.

- Performance Against Key Objectives

Provide a brief summary of how well the project met asset performance and quality objectives. Provide brief summary of other issues such as OSH performance, environmental compliance where appropriate and information readily available.

- Community and Stakeholder Issues & Regulatory Approvals

Provide feedback on the process of obtaining approvals (Developer being responsible for approvals and the Corporation being responsible for the formal Prerequisites to Works).

Provide brief comments on issues with external or internal stakeholders. Comments about the impact of issues such as land matters, environmental, native title or aboriginal heritage can be included here. Also note where community or stakeholder input has been considered in project decision making. Any issues with regard to regulatory approvals may be included here also.

- Highlights and Innovations

Provide brief comments on any highlights or any innovations employed or generated.

- Outstanding Project Completion Actions

List the major outstanding action items, e.g. licences required, commitments to community etc; and who is responsible. Any outstanding items from the punch list or defects and omissions list shall be included here also.

Land Matters cannot be unresolved; any easement, reserve, freehold lot must be finalised as part of this Closeout Report. PPC and any applicable recoup to the Developer is dependent on the acceptance of this Closeout Report.

| Project Completion Action Required | Person Responsible | When Required | Comments |
| --- | --- | --- | --- |

- Lessons Learned Items

A statement of lessons learned and recommended actions that would assist in carrying out future similar projects is required. Try to include positive aspects that could be recommended to be applied to other projects. Open to all stakeholders. Adjust columns as required.

| Item | Recommended Action | Recommended by |
| --- | --- | --- |

- Defects Liability Period

Provide brief comments on defects liability periods for various elements of the project

| Commencement Date | Expiry Date |
| --- | --- |

- Warranties

Provide brief comments on warranties for works completed over the course of the project

| Works Component | Date | Contractor |
| --- | --- | --- |

### Appendices

### Appendix 1 – Works Paid Confirmation Letter

Letter from the developer confirming all costs for the works have been paid.

### Appendix 2 – Water Corporation cost summary template

### Water Corporation cost estimate spreadsheet updated with actual costs

### Appendix 3 – Construction Contract Variation Table

A table highlighting any variations to the original construction contract fee (include the original fee)

### Appendix 4 – Engineering Fees and Variation Table

A table highlighting any variations to agreed engineering fees

### Appendix 5 – Engineering Fee Tax Invoices

A copy of the engineering fee tax invoices and receipts of payment for specialist providers listed in Appendix 3.

### Appendix 6 – Construction Engineer Statement

Statement from the construction engineer confirming the works have been constructed in accordance with the relevant manuals and documents.

### Appendix 7 – Land Restoration Letter

A letter from the construction engineer confirming that the restoration has been completed to the satisfaction of the affected landowners/authorities

### Appendix 8 – Land Matters, Survey Plan and Land Transfer Documentation

MUST BE RESOLVED e.g. a survey plan showing easements benefit to the Corporation or Documentation for transfer of land in favour of the Corporation. Include a Copy of the Landgate Deposited Plan showing reserve or easement.

### Appendix 9 – Design Compliance Report

Include completed Design Compliance Report

### Appendix 10 – Warranties

Include any warranties for works completed over the course of the project

### Appendix 11 – Construction Schedule/Timeline

Include a completed construction schedule with actual dates for completion of various steps

### Appendix 12 – As Constructed Drawings List

Include a list of as the constructed drawings for the project, as accepted by the Water Corporation’s Design Manager.

### Appendix 13 – Project Photos

Include relevant project photos of the project at various stages of completion

### Appendix 14 – Developer Project Monthly Progress Reports

### Appendix 15 – Closeout Report Administration Sheet

Complete the form below

Project Manager

| Closeout Report is: | New | Revised revision #: insert revision # |  |
| --- | --- | --- | --- |

Tick the asset type or types that the project should be categorised as:

| Asset Type | Tick | Asset Type | Tick |
| --- | --- | --- | --- |
| Waste Water Treatment Plants |  | Minor Pumping Stations |  |
| Effluent Disposal Systems |  | Tanks & Reservoirs |  |
| Ocean Outfalls |  | Supply, Trunk & Distribution Mains |  |
| Main Sewers |  | Reticulation Mains |  |
| Main Sewer Pumping Stations |  | Main Drains & Detention Basins |  |
| Reticulation Sewers |  | Main Drainage Pump Stations |  |
| Sewer Pumping Stations |  | SCADA & Telemetry Systems |  |
| Dams (incl. Pipeheads) |  | Depots, Offices & Buildings |  |
| Bores & Borefields |  | Computing Systems (Hardware & Software) |  |
| Water Treatment Plants (incl. dosing plants) |  | Other |  |
| Major Pumping Stations |  |  |  |
| Project Manager’s Name: Date: |  |  |  |

### Appendix 16 – Closeout Report Review Response Table